## How to use
FXR60/90 — Pending problems tracker
Purpose
Separate tracker for items that still have problems or need work. Main effort sheet: FXR90-Examples-Effort-Effectiveness.xlsx
Priority legend
Priority | Meaning
1 | Need to work — not finalized
2 | Discuss / known issue — blocked on QA/dev
3 | Schema / deferred — postponed or tier cleanup
4 | NEED LIVE TEST — draft ready, verify on reader
5 | Build gap — missing example packs
6 | Product note — documented; keep for reference
Created
2026-08-11

## Pending problems
Priority | Category | Method | Endpoint | Problem / status | Blocked on | Can work now? | Notes
2 | Discuss / known issue | DELETE | /cloud/certificates/{certname} | Unclear if type query/param required on DELETE | QA | No
2 | Discuss / known issue | GET | /cloud/caCertificates | Finalize caCertificates examples | Mayur | No | GET/PUT/DELETE together
2 | Discuss / known issue | PUT | /cloud/caCertificates/{caname} | Finalize caCertificates examples | Mayur | No
2 | Discuss / known issue | DELETE | /cloud/caCertificates/{caname} | Finalize caCertificates examples | Mayur | No
3 | Schema / deferred | GET | /cloud/config | GPIO-LED response schema is wrong: oneOf has only a string branch ("NOT_CONFIGURED"), but the live GET returns an object (GPODefaults/LEDDefaults/RADIO_START/RADIO_STOP/TAG_READ, or {}). Response example does not validate against it. | — | Yes | Examples DONE 2026-08-11: GET now has one live example (full_configuration) in REST + MQTT; PUT pack done (11). Fix: add GPIOLEDConfig.v1 as an object branch to the oneOf in RestDeveloperfile.yaml ~line 1298. Not applied — schema change pending approval.