## Questions
Column I is the schema check vs openAPISpec 11.yaml (schema only). Dated 2026-09-07. Updated (fixed) rows were removed. Column H is empty on new rows — for the developer reply.
# | REST API | MQTT | Topic | What the reader does | What your spec says | Question for you | Your reply (please fill) | Schema check | Note (schema only)
1 | GET /cloud/mode and PUT /cloud/mode | get_mode / set_mode | GPI ports 1–4 | Four GPI ports: 1, 2, 3, and 4. | When inventory starts or stops on a GPI, only port 1 or 2 is allowed. | Could you please include ports 3 and 4 as valid options for starting/stopping inventory on a GPI, to match GET /cloud/gpi, which already lists all four ports? | updated schema | Said updated — not in schema | They wrote updated schema. gpi.v1.port ~line 9575 is still maximum: 2. GET/PUT /cloud/mode still use this via radioStartConditions / radioStopConditions / antennaStopCondition.
2 | GET /cloud/mode and PUT /cloud/mode | get_mode / set_mode | READER_LOCATION in tagMetaData | READER_LOCATION works in tagMetaData on GET /cloud/mode and PUT /cloud/mode. | READER_LOCATION is not listed as a valid tagMetaData value. | Could you please add READER_LOCATION to the documented tagMetaData values for GET /cloud/mode and PUT /cloud/mode, since it is supported on the reader? | updated schema | Said updated — not in schema | They wrote updated schema. tagMetaData.v1 enum ~line 10138 still has no READER_LOCATION.
3 | PUT /cloud/network | set_network | Where enable lives | Wi-Fi on/off: mlan0.enable. 802.1X on/off: eth0.security.enable. Wi-Fi security on/off: mlan0.accesspoint.security.enable. | Wi-Fi on/off is mlan0.accesspoint.enable. The two security enable fields are not listed. | Can you match the reader? | We don’t support enable for the security fields.no update required | Valid reason | They said they do not support enable on the security fields and no update is required. Schema still has no eth0.security.enable or mlan0.accesspoint.security.enable.
4 | GET /cloud/readerCapabilities | get_readerCapabilities | supportedPowerSource includes unused DC, inconsistent naming | Only PWR_BRICK, POE, and POE+ are used. DC is not supported on FXR60/FXR90. | supportedPowerSource enum lists DC, POE, POE+, POWERBRICK, BATTERY -- includes the unused DC, and spells the brick option POWERBRICK instead of PWR_BRICK (inconsistent with GET /cloud/status). | Could you remove DC from the supportedPowerSource enum and rename POWERBRICK to PWR_BRICK, to align with GET /cloud/status and actual device behavior? | Since the code is common for starfish and vulcan we cannot remove DC from the schema..i have upated saying PWR_BRICK,POE and POE+ alone supported for Fxr90/60 | Valid reason | They cannot remove DC (shared Starfish/Vulcan schema). They documented FXR60/90 as POE, POE+, POWERBRICK. Enum still has DC and POWERBRICK.
5 | PUT /cloud/certificates | set_updateCertificate | Multiple issues: field naming, authenticationType NONE, url port, and other untested fields | Username and password work with authenticationOptions; options does not work. Separately, authenticationType: NONE (with or without an empty authenticationOptions object) is rejected with "INVALID USER NAME" for an HTTPS download URL -- only authenticationType: BASIC with real, non-empty credentials gets past this check (confirmed with 4 isolated payload variations). A url with an explicit port -- even the correct default port, e.g. https://host:443/path -- is rejected with "INVALID IPADDR OR DOMAIN NAME", isolated with a single-variable test against an already-working URL. Also reported (not yet isolated with live tests): the inline certificate content fields (CACertificateFileContent, publicKeyFileContent, privateKeyFileContent) and headers with an Authorization: Bearer value do not appear to work as documented. | openAPISpec 10.yaml (line 5293) lists the credentials field as options. The authenticationType enum lists NONE as valid, implying no credentials are required. The url pattern (^https://.+ etc.) does not forbid a port number, and a host:port URL is valid per RFC 3986. The inline certificate fields and headers are documented as supported options in the request schema. | 1) Can you change the spec to authenticationOptions (not options)? 2) Is authenticationType: NONE actually supported for HTTPS downloads? If not, should it be removed from the enum? 3) Is a port number supported in url at all? If not, please note this restriction, and consider correcting the error message, which blames the IP/domain even though those were proven valid in our test. 4) Could you also confirm whether the inline certificate content fields and headers.Authorization are actually functional for certificate installation? | Actually the code supports both options and authentication options. Will test this more and update the schema. | Valid reason | They said the code supports both options and authenticationOptions and will test again. Schema still has options only (~line 5335).
6 | PUT /cloud/os | set_os | Field naming (options vs authenticationOptions), headers.Authorization, and mTLS client certificate not honored during firmware download | Username and password work with authenticationOptions; options does not work. Tested on a real FXR60 with a live firmware server. BASIC authentication works end to end (downloaded, flashed, rebooted, reported readerApplication 5.0.5-6). With authenticationType: NONE and headers: {Authorization: "Bearer ..."} against a Bearer-only server, the reader instead sent Basic authentication for the file request; the Bearer-only server returned HTTP 401 and the reader never started flashing. Separately, with verifyPeer/verifyHost: true, installedCertificateType: "client", and installedCertificateName set to an already-installed certificate ("scenario-basic", confirmed present via GET /cloud/certificates), the mTLS handshake to the firmware server failed (server log: PEER_DID_NOT_RETURN_A_CERTIFICATE) -- the reader never presented the selected client certificate, and firmware download did not start. In both failing cases, the REST call itself still returned an HTTP 200 acknowledgment. | openAPISpec 10.yaml (line 7348) lists the credentials field as options. headers is documented as "Optional HTTP headers to include in the download request (e.g. Authorization)" -- implying a supplied Authorization header is sent as given. installedCertificateType/installedCertificateName are documented as selecting an already-installed certificate "for client TLS authentication during the download." | Can you change the spec to authenticationOptions (not options) for PUT /cloud/os? Can you confirm whether headers.Authorization and installedCertificateType/installedCertificateName are actually implemented for PUT /cloud/os firmware downloads? In this test the reader ignored the supplied Bearer header (always sending Basic instead) and never presented the selected client certificate during mTLS, even though BASIC-only authentication worked correctly end to end. | Actually the code supports both options and authentication options..Authorization and installedCertificateType/installedCertificateName are actually implemented for PUT /cloud/os firmware downloads.I will check on the mtls part and update. | Valid reason | Same as certificates: they said both keys work and they will recheck mTLS. Schema still has options only (~line 7297).
7 | GET /cloud/timeZone and PUT /cloud/timeZone | get_timeZone / set_timeZone | GET returns a different value format than PUT accepts | Sending PUT with a GMT-style value from the documented enum (e.g. "(GMT+05:30) Chennai, Kolkata, Mumbai, New Delhi") succeeds. The next GET returns "Asia/Kolkata" -- an IANA-style identifier that is not in the documented GET enum at all. | Both GET and PUT list the same ~150 GMT-style display strings as the allowed enum. | Are GET and PUT meant to use the same vocabulary? If GET always returns IANA identifiers regardless of what was set, the GET enum needs to be documented differently (or removed in favor of a plain string), since it currently does not match what the reader returns. | since IANA is the newer format we will return in this format…but the PUT will accept both legacy GMT and newer IANA formats to be flexible and backward compatible. | Valid reason | They said GET returns IANA and PUT accepts GMT + IANA. They did not rewrite the enum. getTimeZone/setTimeZone enums are still GMT-style.
8 | PUT /cloud/mode | set_mode | wordCounter vs wordCount | wordCount works in the READ access config. wordCounter is rejected (HTTP 422): "wordCount must be included in access-config object for read". After renaming the field, TID is returned in accessResults. | The READ config requires wordCounter. The with_accesses example also uses wordCounter. MQTT set_mode uses the same name. The description on wordCounter repeats "WordPtr Field" (that is wordPointer). | Can you change the spec field name from wordCounter to wordCount so it matches the reader? |  | Not in spec 11 | access_cmd_read.v1 (~line 9924) still has required property wordCounter. Live reader 5.0.7 accepts only wordCount. Feature works after the rename.
9 | PUT /cloud/bleConfig (GET /cloud/bleConfig response: generic filters) | set_bleConfig / get_bleConfig | generic filter field casing | The generic filter accepts only lowercase names: address, addressType, name, alias. Capital names Address, AddressType, Name, Alias are rejected (HTTP 422): unknown or unexpected field. Isolated by bisection on reader 5.0.7. After lowercasing, the same body is stored and read back. | PUT schema, PUT example enable_with_protocols, and GET schema/example all use Address, AddressType, Name, Alias. Those look like BLE output event names pasted into the input filter. | Can you change the generic filter field names to address, addressType, name, alias in both the schema and the examples (PUT enable_with_protocols and GET)? Same names appear on GET /cloud/bleConfig. |  | Not in spec 11 | PUT generic properties ~line 8476 and example ~line 8565 still capital. GET generic properties ~line 8752 and example ~line 8803 still capital. Live reader 5.0.7 accepts lowercase only.
10 | PUT /cloud/bleConfig | set_bleConfig | four required ble fields vs description / short examples | PUT fails if any of these four is missing: enable, scanIntervalSec, protocols, additionalFilters. A short body such as {"ble":{"enable":true}} is rejected. additionalFilters may be {}. protocols may list only one protocol. All four keys must still be present. | The schema required list already has those four fields. The operation description still says only ble.enable is required and the other fields are optional. That wording does not match the schema or the reader. | Can you change the description so it says all four fields are required (enable, scanIntervalSec, protocols, additionalFilters), matching the schema and the reader? Please also check that no example omits any of the four — a short example will fail on the device. |  | Not in spec 11 | required list ~line 8275 already has the four fields. Description ~line 8258 still says only enable is required and the rest are optional.
11 | PUT /cloud/impinjGen2X | set_impinjGen2X | only one feature per request | Any two of fastID, tagProtect, tagFocus, tagQuieting in one request return HTTP 422: Only one Impinj Gen2X feature can be configured at a time. All four are exclusive. Tested on reader 5.0.7 (five combinations). | v3.0.0 / spec 11 removed the mutually exclusive table. The PUT description does not say only one feature is allowed. An older spec said only fastID, tagFocus, tagQuieting conflict and tagProtect could be mixed. That is not what the reader does. | Can you document that exactly one of fastID, tagProtect, tagFocus, or tagQuieting is allowed per request? Combining any two is rejected. Please restore a mutual-exclusion note covering all four features. |  | Not in spec 11 | Live 2026-09-06. Spec 11 PUT description mentions applyImpinjGen2X but no one-feature rule. Schema allows more than one property (minProperties: 1 only).